## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-CV-DW-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0059 |  |  | Transmital Date: 22-AUG-2021
Document Title: Standard Drawing For Electrical Cable Trench |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-0059 |  |  | Transmital Date: 22-AUG-2021
[5 empty] | CRS No:NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0004-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اين نقشه ها مطابق نقطه نظرات بخش برق مي بايست بطور كامل بازنگري و مجدد ارائه شوند: نقشه هاي تيپ میبایست مطابق با استانداردهای IPS-D-EL-209 و IPS-D-EL-210 اصلاح گردند. |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | نقشه دستگردانی داخلی شده و مغایرتی با مدارک بخش برق ندارد و مطابق با استاندارهای ذکر شده نیز میباشد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: