## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-PY-0005_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0920 |  |  | Transmital Date: 9 May 2022
Document Title:Data Sheets For F&G Detectors & Equipment |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-0920 |  |  | Transmital Date: 9 May 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0016_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرک F&G Cause & Effect به مدارک مرجع اضافه گردد. |  | 1401-2294-104549 | 1401/03/25 | مدرک مطابق خواست کارفرمای محترم اصلاح گردید.
2 | Zone تجهیزات مطابق Spec. مورد بازنگری قرار گیرد. |  | 1401-2294-104549 | 1401/03/25 | مطابق مدارک پروژه ZONE 2 برای تجهیزات در نظر گرفته شده است.
3 | مشخصه SIL تجهیزات مورد بازنگری قرار گیرد. |  | 1401-2294-104549 | 1401/03/25 | مدرک مطابق خواست کارفرمای محترم اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 20 Feb 2022 |  |  |  |  | Date: