## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-PY-0001-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0491 |  |  | Transmital Date:01/22/2022
Document Title:Unit Plot Plan Drawing |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-0491 |  |  | Transmital Date:1/22/2022
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-PI-PY-0001-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بند 7 صورتجلسه: تراز ارتفاعی ساختمان ها و پیاده رو در مدرک درج نشده است |  | 00/2294/424188 | 1400/12/05 | احتراما اعمال گردید
2 | بند 9 صورتجلسه: مطابق با این بند می بایست فضای سبز در نظر گرفته شود که لحاظ نشده است. |  | 00/2294/424188 | 1400/12/05 | احتراما فضای سبز در انتهای پروژه با نظر بهره بردار محترم و با طرح خروجی EIAنهایی خواهد شد
3 | بند 15 صورتجلسه: موارد مندرج در این بند لحاظ نشده است |  | 00/2294/424188 | 1400/12/05 | احتراما اعمال گردید
4 | بند 20 صورتجلسه: تراز ارتفاعی طراحی نشده و در مدرک مشخص نمی باشد |  | 00/2294/424188 | 1400/12/05 | احتراما اعمال گردید
5 | جهت ترسیم نمای ساختمان سوئیچگیر لازم است بر اساس موارد مندرج در نامه 377543 مورخ 1400/11/03 اقدام گردد. |  | 00/2294/424188 | 1400/12/05 | احتراما اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: G.Khosravizadegn/ F.Amiri/ | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 24-Jan-2022 |  |  |  |  | Date: 24-Jan-2022