## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DG-0009_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1026 |  |  | Transmital Date: 30 May 2022
Document Title: F&G Cause and Effect Diagram for Process Area |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1026 |  |  | Transmital Date: 30 May 2022
[5 empty] | CRS No: NISOIC-CRS-BK-GCS-PEDCO-120-IN-DG-0009_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اظهار نظر در خصوص مدرک فوق، منوط به نهایی شدن نقشه جانمایی سیستم F&G و سایر مدارک مرتبط می باشد. |  | 01/2294/177038 | 1401/5/2023 | مدرک مطابق آخرین نسخه از مدارک مرجع اصلاح و ارسال گردید.
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 5/21/2022 |  |  |  |  | Date: