## Cover Sheet
|  |  | Quality Surveillance Report |  | Doc. No.: | IMS-QC-FO-89-R0
[5 empty] | Rev No.: | 0
Rev Date.:
[5 empty] | Report No: | BK-0006
Project: | BINAK
ContractType: |  | EPC
Location: | GENAVEH
Owner: | PEDCO
Start of Project:
End of Project:
Report Duration: From 20/06/1401 to 20/07/1401
PHOTO
Quality representative |  |  |  | Project QA/QC Manager
Name: |  |  |  | Name:
Date: |  |  |  | Date:
Signature: |  |  |  | Signature:

## General Data
|  |  | Quality Surveillance Report (General Data) | [17 empty] | Doc. No.: | IMS-QC-FO-89-R0
[21 empty] | Rev No.: | 0
[21 empty] | Page No: | 1 of 7
Item No. | Contractor | KOM | QC Document Review and Control |  |  |  |  | PIM | Site Monthly QA/QC Meeting |  | Office Bi-weekly QA/QC Meeting |  | Data Controling Software and Info Structures |  |  | List of Audits / Inspection Activities Performed or Observed Within This Period |  |  |  |  | FDB
|  |  | MDR | Total MDR QC Docs | Issued MDR QC Docs | QCP | PQP |  | Date | MOM No. | Date | MOM No. | RT Digitalizing System | Weld Joint Control System | Work Site Activities Master Data Bank | Subcontractor/Vendor/Supplier/Manufacturer/Service Provider | Location | ActivityType | Activity Scope | Remark | Construction | Precomm. & Comm.
1 | 053-073-9184 | Done and Closed | Approved | 43 | 18 | Approved | Under Processing | Done and Closed | 1400/10/07 | 1400/009 | 1400/04/12 | 0003
2 | [10 empty] | 1400/11/13
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
Abbreviation: KOM: Kick Off Meeting PIM: Pre Inspection Meeting MDR: Master Document Register QC: Quality Control Docs: Documents QCP: Quality Control Plan PQP: Project Quality Plan QA: Quality Assurance MOM: Minute Of Meeting RT: Radiography Test FDB: Final Data Book

## CWAS
|  | Quality Surveillance Report Contractor Work Site Activity and Status (CWAS) | [8 empty] | Doc. No.: | IMS-QC-FO-89-R0
[11 empty] | Rev No.: | 0
[11 empty] | Page No: | 2 of 7
No. | Contractor Name | Working Descipline | Current Worksite Activities (Remain & Ongoing) | No. of Site Resident QC-Man | Total Required Resident QC-Man | Next Month Activity Plan |  |  | Any working Concern or Outstanding
[6 empty] | Sub Contractor | Location | Work Site Activity | Issue (Discrepancies or Deviation) |  | Company or Company Rep. Action | Action Taken by Contractor
1 |  | Civil | عملیات تخریب و جمع آوری فنس و دیواره زیرین مربوطه در کلاستر | 1 | 1 | مشارکت هیرگان انرژی - طرح و بازرسی | کلاستر | احداث فنس جدید |  |  |  |  | CM | Under Process
|  | Civil | عملیات تسطیح و رگلاژ جاده دسترسی چاه 14 |  |  |  | چاه 14 | عملیات خاکریزی جاده دسترسی چاه 14 |  |  |  |  | FIR | Resolved
2 |  | Structure | [10 empty] | Note
N/A
IWR
3 |  | Architecture
4 |  | Pipeline
5 |  | Piping
6 |  | Mechanic
7 |  | Electrical
8 |  | Instrument
9 |  | Telecomm.
Abbreviation:
| CM= Company Memorandum |  | NOTE= Any Form of Warning |  |  |  |  | IWR=TPI Weekly Report |  | QC: Quality Control
| FIR=Field Inspection Report |  | N/A= Not Applicable or No Action |  |  |  |  | NCR=Non Conformity Report |  | REP: Representative

## Civil Work
|  | Quality Surveillance Report (Civil Work)مهر ماه 1401 | [23 empty] | Doc. No.: | IMS-QC-FO-89-R0
[26 empty] | Rev No.: | 0
[26 empty] | Page No: | 3 of 7
Item No. | Contractor | Civil | Location | Documentation Status | MRI | FIN | [7 empty] | FIR |  | Surveying Report (Bench mark,...) |  | Earth Work |  | General Reinforcing, Concrete work |  | TQ |  | NCR |  | QC Record/QC Data Book | As Built Drawing
|  | Area/ Unit |  | ITP |  | Up to This Month |  |  |  | This Month |  |  |  | Up to This Month | This Month | Checking of Report | Client Review | Overal Inspection / Supervision Result | Final Client Approval | Overal Inspection / Supervision Result | Final Client Approval | # Issued | # Closed | # Issued | # Closed
[6 empty] | Received | Accepted | Canceled/Rejected | Commented | Received | Accepted | Canceled/Rejected | Commented
1 |  | W018S/Area G | MUD Channel Area | Approved | Done | [8 empty] | 11 | 0 | Not Done | Not Done | Accepted | Reviewed and Signed | Accepted | Reviewed and Signed | 0 | 0 | 0 | 0 | Under Processing | Under Processing
2 |  | W018S/Area H | Access Road To Burn Pit | Approved | [9 empty] | 2 | 0 | Not Done | Not Done | Accepted | Reviewed and Signed | N/A | N/A | 0 | 0 | 0 | 0 | Under Processing | Under Processing
3 |  | W018S/Area I | Waste Pit | Approved | Done | [8 empty] | 6 | 0 | N/A | N/A | Accepted | Reviewed and Signed | N/A | N/A | 0 | 0 | 0 | 0 | Under Processing | Under Processing
4 |  | W018S/Area J | Clear Pit | Approved | Done | [8 empty] | 6 | 0 | N/A | N/A | Accepted | Reviewed and Signed | N/A | N/A | 0 | 0 | 0 | 0 | Under Processing | Under Processing
5 |  | W018S/Area K | Water Pool | Approved | Done | [8 empty] | 5 | 0 | N/A | N/A | Accepted | Reviewed and Signed | N/A | N/A | 0 | 0 | 0 | 0 | Under Processing | Under Processing
6 |  | W018S/Area L | Treatment Area | Approved | Done | [8 empty] | 10 | 0 | Not Done | Not Done | Accepted | Reviewed and Signed | Accepted | Reviewed and Signed | 0 | 0 | 0 | 0 | Under Processing | Under Processing
7 |  | W018S/Area M | Burn Pit | Approved | [9 empty] | 3 | 0 | N/A | N/A | Accepted | Reviewed and Signed | N/A | N/A | 0 | 0 | 0 | 0 | Under Processing | Under Processing
8 |  | W018S/Area S | Disposal Area | Approved | Done | [8 empty] | 6 | 0 | N/A | N/A | Accepted | Reviewed and Signed | N/A | N/A | 0 | 0 | 0 | 0 | Under Processing | Under Processing
9 |  | W018S | Access Road To Well | Approved | [9 empty] | 2 | 0 | Not Done | Not Done | Accepted | Reviewed and Signed | N/A | N/A | 0 | 0 | 0 | 0 | Under Processing | Under Processing
10 |  | W018S | Oil Trap | Approved | Done | [8 empty] | 8 | 0 | Not Done | Not Done | Accepted | Reviewed and Signed | Accepted | Reviewed and Signed | 0 | 0 | 0 | 0 | Under Processing | Under Processing
11 |  | Culvert Road W028 | KM 0+195 | Approved | Done | 32 | 32 | 0 | 0 | 4 | 0 | 0 | 0 | 32 | 4 | No Comment | Reviewed and Signed | Not Done | Not Done | Not Done | Not Done | 0 | 0 | 0 | 0 | Under Processing | Under Processing
12 |  | Culvert Road W028 | KM 0+344 | Approved | Done | 25 | 25 | 0 | 0 | 11 | 4 | 0 | 0 | 25 | 11 | No Comment | Reviewed and Signed | Not Done | Not Done | Not Done | Not Done | 0 | 0 | 0 | 0 | Under Processing | Under Processing
13 |  | Culvert Road W028 | KM 0+511 | Approved | Done | 36 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | No Comment | Reviewed and Signed | Not Done | Not Done | Not Done | Not Done | 0 | 0 | 0 | 0 | Under Processing | Under Processing
14 |  | W028/Area D | Gravel Area | Approved |  | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | No Comment | Reviewed and Signed | Not Done | Not Done | N/A | N/A | 0 | 0 | 0 | 0 | Under Processing | Under Processing
15 |  | W028/Area R | Water Pool | Approved | Not Done | 10 | 8 | 0 | 0 | 0 | 2 | 0 | 0 | 10 | 0 | No Comment | Reviewed and Signed | Not Done | Not Done | N/A | N/A | 0 | 0 | 0 | 0 | Under Processing | Under Processing
16 |  | W028/Area S | Burn Pit | Approved |  | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | No Comment | Reviewed and Signed | Not Done | Not Done | N/A | N/A | 0 | 0 | 0 | 0 | Under Processing | Under Processing
17 |  | W028/Area A | Cellar | Approved | Done | 17 | 8 | 0 | 0 | 0 | 2 | 0 | 0 | 17 | 0 | No Comment | Reviewed and Signed | Not Done | Not Done | Not Done | Not Done | 0 | 0 | 0 | 0 | Under Processing | Under Processing
18 |  | W028/Area B | Concrete Pad | Approved | Done | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 2 | Not Done | Not Done | Not Done | Not Done | Not Done | Not Done | 0 | 0 | 0 | 0 | Under Processing | Under Processing
19 |  | W028/Area E | West Septic | Approved | Done | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Not Done | Not Done | Not Done | Not Done | Not Done | Not Done | 0 | 0 | 0 | 0 | Under Processing | Under Processing
20 |  | W028/Area E | East Septic | Approved | Done | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Not Done | Not Done | Not Done | Not Done | Not Done | Not Done | 0 | 0 | 0 | 0 | Under Processing | Under Processing
21 |  | W028/Area C | Fuel Tank | Approved | Done | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Not Done | Not Done | Not Done | Not Done | Not Done | Not Done | 0 | 0 | 0 | 0 | Under Processing | Under Processing
22 |  | W028/Area k | Water Channel | Approved |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Not Done | Not Done | Not Done | Not Done | Not Done | Not Done | 0 | 0 | 0 | 0 | Under Processing | Under Processing
23 |  | W028 / Area G | Treatment Area | Approved | Done | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | Not Done | Not Done | Not Done | Not Done | Not Done | Not Done | 0 | 0 | 0 | 0 | Under Processing | Under Processing
24 |  | W028 / Area I | Dewatering Area | Approved | Done | 10 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 10 | 0 | Not Done | Not Done | Not Done | Not Done | Not Done | Not Done | 0 | 0 | 0 | 0 | Under Processing | Under Processing
25 |  | W028 / Area Q | Waste Pit | Approved | Not Done | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | Not Done | Not Done | Not Done | Not Done | N/A | N/A | 0 | 0 | 0 | 0 | Under Processing | Under Processing
26 |  | W028 / Area J | OBM Waste Pit | Approved | Done | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 16 | Not Done | Not Done | Not Done | Not Done | Not Done | Not Done | 0 | 0 | 0 | 0 | Under Processing | Under Processing
27 |  | W028 / Area K | Diversion Channel For Location | Approved |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | Not Done | Not Done | Not Done | Not Done | Not Done | Not Done | 0 | 0 | 0 | 0 | Under Processing | Under Processing
28 |  | W028 / Area W | Oil Trap | Approved | Done | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Not Done | Not Done | Not Done | Not Done | Not Done | Not Done | 0 | 0 | 0 | 0 | Under Processing | Under Processing
* Please Specify any informations or other stages of works, locations, units,… , as required.
Abbreviation: QC: Quality Control ITP: Inspection Test Plan MRI: Material Receive Inspection FIN: Field Inspection Notice FIR: Field Inspection Report TQ: Technical Query NCR: Non Conformity Record N/A: Not Applicable

## Structural Work
|  | Quality Surveillance Report (Structual Work) | [29 empty] | Doc. No.: | IMS-QC-FO-89-R0
[32 empty] | Rev No.: | 0
[32 empty] | Page No: | 4 of 7
Item No. | Contractor | Structural * | Documentation Status |  |  |  |  | MRI | FIN | [7 empty] | FIR |  | WQT | Welder Test Certificate | NDT | PWHT | DT | Bolt Tightening | Painting | Final Inspection Result | Client Approval | TQ |  | NCR |  | QC Record/QC Data Book | As Built Drawing
|  | Area/ Unit/ Drawing No./ Location * | ITP | WPS/PQR | NDT | PWHT | Sandblast & Painting |  | Up to This Month |  |  |  | This Month |  |  |  | Up to This Month | This Month | [9 empty] | # Issued | # Closed | # Issued | # Closed
[9 empty] | Received | Accepted | Canceled/Rejected | Commented | Received | Accepted | Canceled/Rejected | Commented
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
* Please Specify any informations or other stages of works, locations, units,… , as required.
Abbreviation: FIN: Field Inspection Notice FIR: Field Inspection Report QC: Quality Control ITP: Inspection Test Plan WPS: Welding Procedure Specification PQR: Procedure Qualification Record NDT: Non Destructive Test PWHT: Post Weld Heat Treatment MRI: Material Receive Inspection WQT: Welder Qualification Test DT: Dimension Test TQ: Technical Query NCR: Non Conformity Record N/A: Not Applicable

## Piping & Pipeline
|  | Quality Surveillance Report (Piping & Pipeline) | [61 empty] | Doc. No.: | IMS-QC-FO-89-R0
[64 empty] | Rev No.: | 0
[64 empty] | Page No: | 5 of 7
Item No. | Contractor | Piping & Pipline | Documentation Status | [5 empty] | MRI | FIN | [7 empty] | FIR |  | WQT | Total Weld |  | Fit Up |  |  |  | Welding |  |  |  | VT |  |  |  | MT/PT |  |  |  | RT |  |  |  | UT/PAUT |  |  |  | Repair Rate |  |  |  | Local PWHT | Hardness |  | Pigging |  | Hydrotest | Leak Test | Coating |  | TQ |  | NCR |  | QC Record/QC Data Book | As Built Drawing
|  | Area/ Unit/Line No/ Drawing No./ Location * | ITP | WPS/PQR | NDT | Hydrotest | PWHT | Coating |  | Up to This Month |  |  |  | This Month |  |  |  | Up to This Month | This Month |  | Per Joint | Per Dia Inch | Per Joint |  | Dia Inch |  | Per Joint |  | Dia Inch |  | Per Joint |  | Dia Inch |  | Per Joint |  | Dia Inch |  | Per Joint |  | Dia Inch |  | Per Joint |  | Dia Inch |  | Per Joint |  | Dia Inch |  |  |  | Test Package | Cleaning | Deformation, Geometric |  |  | Pipeline/Pipe Body Coating | Field Joint Coating | # Issued | # Closed | # Issued | # Closed
[10 empty] | Received | Accepted | Canceled/Rejected | Commented | Received | Accepted | Canceled/Rejected | Commented | [5 empty] | Up to This Month | This Month | Up to This Month | This Month | Up to This Month | This Month | Up to This Month | This Month | Up to This Month | This Month | Up to This Month | This Month | Up to This Month | This Month | Up to This Month | This Month | Up to This Month | This Month | Up to This Month | This Month | Up to This Month | This Month | Up to This Month | This Month | Up to This Month | This Month | Up to This Month | This Month
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
* Please Specify any informations or other stages of works, locations, units,… , as required.
Abbreviation: FIN: Field Inspection Notice FIR: Field Inspection Report QC: Quality Control ITP: Inspection Test Plan WPS: Welding Procedure Specification PQR: Procedure Qualification Record UT: Ultrasonic Test PAUT: Phased Array Ultrasonic Test RT: Radiography Test MT: Magnetic Test PT: Penetration Test NDT: Non Destructive Test PWHT: Post Weld Heat Treatment MRI: Material Receive Inspection WQT: Welder Qualification Test VT: Visual Test TQ: Technical Query NCR: Non Conformity Record N/A: Not Applicable

## Mech. Work, EL, IN, TC
|  | Quality Surveillance Report (Mech. Work, EL, IN, TC) | [30 empty] | Doc. No.: | IMS-QC-FO-89-R0
[33 empty] | Rev No.: | 0
[33 empty] | Page No: | 6 of 7
Item No. | Contractor | Mechanical, Electrical, Instrument, Telecom.** | Documentation Status | MRI | FIN | [7 empty] | FIR |  | Installation Inspection | [8 empty] | Preservation | TQ |  | NCR |  | Final Inspection Result | Client Approval | SAT | SIT | QC Record/QC Data Book | As Built Drawing
|  | Area/ Unit/ Line No./Drawing No./ Location * | ITP*** |  | Up to This Month |  |  |  | This Month |  |  |  | Up to This Month | This Month | Foundation | Marking/Tagging/Name Plate | location/Position/Routing Verification | Visual Inspection | DT | Bolt Tightening |  | Earthing | P & ID Mark Up |  | # Issued | # Closed | # Issued | # Closed
[5 empty] | Received | Accepted | Canceled/Rejected | Commented | Received | Accepted | Canceled/Rejected | Commented | [8 empty] | Cathodic Protection
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
* Please Specify any informations or other stages of works, locations, units,… , as required.
**This sheet include only manufactured items which is expected to be installed at site witout any further fabrication, welding or any hot working or cold forming activities.
***This ITP refers to all tests and performance requirements expected to be done during installation and site approval test (SAT).
Abbreviation: FIN: Field Inspection Notice FIR: Field Inspection Report QC: Quality Control ITP: Inspection Test Plan MRI: Material Receive Inspection DT: Dimension Test TQ: Technical Query NCR: Non Conformity Record SAT: Site Acceptance Test SIT: Site Integration Test P & ID: Piping & Instrumentation Diagram N/A: Not Applicable

## Precomm. & Comm.
|  | Quality Surveillance Report (Precommissioning & Commissioning) | [15 empty] | Doc. No.: | IMS-QC-FO-89-R0
[18 empty] | Rev No.: | 0
[18 empty] | Page No: | 7 of 7
Item No. | Contractor | Precommissioning and commissioning | Documentation Status |  | MC | Punch A | Punch B | PSSR | Calibration Certificate | availability of Materials, Cosumables and Spare Parts for Precommissioning & Commissioning | Precommissioning Check List & Reports | Ready for Commissioning Certificate | Commissioning Check List & Reports | TQ |  | NCR |  | RFSU | QC Record/QC Data Book
|  | Area/ Unit/ Line No./Drawing No./ Location * | Commissioning & Operation Instruction Manual | Test Procedure | [9 empty] | # Issued | # Closed | # Issued | # Closed
Punch A
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
* Please Specify any informations or other stages of works, locations, units,… , as required.
Abbreviation: MC: Mechanical Completion PSSR:Pre Start Up Safety Review RFSU: Ready For Start Up QC: Quality Control TQ: Technical Query NCR: Non Conformity Record N/A: Not Applicable

## Sheet1 (hidden)
MR | TBE | PO | KOM/PIM | CR Rating | Document | MRI | Material Traceability | WQT | Welder Test Certificate | Weld Traceability | VT / DT | NDT | PWHT | TQ / NCR | Test Package | Pigging | Hydrotest | Coating | Bolt Tightening | Cathodic Protection | P & ID Mark Up | Final Inspection | FAT | SAT | SIT | IRN | IC | MDB/VDB | Preservation | Checking of Report | Client Review | Activity Type | RT Digitalizing System | Weld Joint Control System | Work Site Activities Master Data Bank | overal Inspection / Supervision Result | Final Client Approval | QC Record/QC Data Book | As Built DWG | Marking/Tagging/Name Plate | MC | Punch A | Punch B | PSSR | Calibration Certificate | availability of Materials, Cosumables and Spare Parts for Precommissioning & Commissioning | Precommissioning Check List & Reports | Ready for Commissioning Certificate
Issued and reviewed by QC | Scored by QC | Placed | Done and Closed | 1 | Under Processing | Done | Monitored | Not Performed | Not Submitted | Monitored | Done and Accepted | Under processing | Done and Accepted |  | Under Processing | Done and Accepted | Done and Accepted | Done and Accepted | Done | Installed and PhisicallyAccepted | Done and Accepted | Done and Accepted | Done and Accepted | Done But Not Satisfactory Result | Done But Not Satisfactory Result | Issued and Accpepted | Issued | Reviewed and Accepted | Performed But Not Accepted By Authorized Parties. | No Comment | Reviewed and Commented | Audit | N/A | N/A | N/A | Accepted | Reviewed and Commented | Submitted and Accepted | Submitted and Accepted | Controled and Accepted | Done and Certified By Authorized Parties | Issued and Cleared | Issued and Cleared | Under Processing | Done and Report Submitted | Controled and Satisfactory result Accepted By Authorized Parties | Performed and Accepted By Authorized Parties | Submitted
Issued but not reviewd by QC | Not scored by QC | Not Placed | Done but Not Closed | 2 | Not issued | Not Done | Not Monitord | Under Processing | Submitted and Approved | Not Monitord | Done But Not Accepted | All Tests Completed But Partially Accepted | Done But Not Accepted |  | Reviewed and Punch List Issued | Not Done | Done But Not Accepted | Done and Partially Accepted | Not Done | Installed But Not PhisicallyAccepted | Done and Commented | Done But Not Accepted | Done But Not Accepted | Done and Certified By Authorized Parties | Done and Certified By Authorized Parties | Issued and Commented | Not Issued | Reviewed and Commented | Performed and Accepted By Authorized Parties. | Commented | Reviewed and Signed | Performing Inspection/Testing | Fully Stablished and Currently In Use | Fully Stablished and Currently In Use | Fully Stablished and Currently In Use | Not Accepted | Reviewed and Signed | Submitted and Commented | Submitted and Commented | Controled and Commented | Done and Commented By Authorized Parties | Issued and Under Corrective Action | Issued and Under Corrective Action | Done and Accepted By Authorized Parties | Not Done | Under Processing | Performed But Need Corrective Action | Not submitted
Issued and reviewed by QC and approved by client |  |  | Not Done | 3 | Approved |  |  | Performed Under Supervision of QC Autorized Rep./TPI | Submitted and Commented | N/A | Not Done | All Tests Completed and Accepted | Not Done |  | Reviewed and Accepted | N/A | Not Done | Not Done | N/A | N/A | Under Processing | Not Done | Not Done | Under Processing | Under Processing | Not Issued | N/A | Under Review Processing | Under Processing | N/A | N/A | Supervising Inspection/Testing | Partially Stablished and Currently In Use | Partially Stablished and Currently In Use | Partially Stablished and Currently In Use | N/A | N/A | Under Processing | Under Processing | Not Done | Under Processing | Not Issued | Not Issued | Not Done | Under Processing | Not Done | Under Processing | N/A
Issued but not reviewd by QC and approved by client |  |  |  | 4 | Approved With Comment |  |  | Supervised and Welder Certificate Reviewed and Accepted |  |  |  | N/A | N/A |  | Reviewed and Rejected |  | N/A | N/A | Under Processing | Under Processing | Not Done |  | N/A | Not Done | Not Done |  |  | Not Issued | Not Done | Not Done | Not Done | Supervising Lab Testing | Under Process | Under Process | Under Process | Not Done | Not Done | Not Submitted | Not Submitted |  | Not Done |  | Conditionaly Accepted | N/A | N/A | N/A | Not Done
[5 empty] | Commented |  |  | Not Required | [6 empty] | Not Submitted |  |  | Under Processing |  | Not Done | N/A |  |  | N/A | N/A |  |  |  | N/A |  |  |  | Not Done | Not Done | Not Done | [5 empty] | N/A
[5 empty] | Rejected | [12 empty] | Done But Not Accepted
N/A