## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0009_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0967 |  |  | Transmital Date: 17 May 2022
Document Title: Data Sheets For Pressure & Safety Relief Valves |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-0967 |  |  | Transmital Date: 17 May 2022
[5 empty] | CRS No: NISCO-CRS-BK-GCS-PEDCO-120-IN-DT-0009_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument Comments
1 | لیست مدارک مرجع لازم ذکر گردد از جمله مدارک زیر: 1. Specification For Pressure Safety Valves(PSV) 2. Instrument & Control System Design Criteria |  | 1401-2294-139962 | 1401/04/23 | اعمال گردید.
2 | داده های محیطی می بایست براساس آخرین ویرایش مدرک Process Basis Of Design مد نظر قرار گیرد. |  | 1401-2294-139962 | 1401/04/23 | بررسی و بازنگری گردید.
3 | داده های پایپینگ با توجه به آخرین ویرایش مدرک PMS بروزرسانی گردید. |  | 1401-2294-139962 | 1401/04/23 | بررسی و بازنگری گردید.
4
5
6
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date:31 May 2022 |  |  |  |  | Date: