## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DT-0004_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1007 |  |  | Transmital Date: 25 May 2023
Document Title: Data Sheets For Pressure & Safety Relief Valves - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1007 |  |  | Transmital Date: 25 May 2023
[5 empty] | CRS No: NISCO-CRS-BK-W007S-PEDCO-110-IN-DT-0004_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument Comments
1 | مدرک زیر به لیست مدارک مرجع اضافه گردد. Instrument & control system design criteria |  | 1401-2294-139937 | 1401/04/23 | اعمال گردید.
2 | داده های محیطی می بایست براساس آخرین ویرایش مدرک PROCESS DESIGN BASIS مد نظر قرار گیرد. |  | 1401-2294-139937 | 1401/04/23 | بررسی و مطابق با آخرین داده های محیطی میباشد.
3 | در خصوص متریال با توجه به اینکه تاکنون PMS مربوطه نهایی نشده است لذا امکان اظهار نظر وجود ندارد لازم به ذکر است همانگونه که در متن مدرک اشاره شده است در صورت بررسی و نهایی سازی متریال با سازنده در مرحله خرید کالا امکان پیشبرد مدرک وجود خواهد داشت. |  | 1401-2294-139937 | 1401/04/23 | ملاحظه شد.
4
5
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 8 Jun 2022 |  |  |  |  | Date: