## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-DT-0006_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1014 |  |  | Transmital Date: 28 May 2022
Document Title: Data Sheets For ON/OFF & Shutdown Valves |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1014 |  |  | Transmital Date: 28 May 2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-NISOC-320-IN-DT-0006_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | داده های محیطی می بایست بر اساس آخرین ویرایش مدرک PROCESS DESIGN BASIS مد نظر قرار گیرد. |  | 1401-2294-177069 | 1401/05/23 | این داده ها بر اساس آخرین مدرک PROCESS DESIGN BASIS به روز رسانی شد.
2 | در صورت متریال مربوط به مدرک 1 به استحضار می رساند با توجه به اینکه تا کنون PMS مربوطه نهایی نشده است، لذا امکان اظهار نظر وجود ندارد. خاطر نشان می سازد اجزایی که با سیال در ارتباط هستند، (Wet Part) میبایست دارای جنس مشابه و متناسب با شرایط خوردگی سیال در نظر گرفته شود. پس از نهایی سازی PMS مدرک مجدد ارسال گردد. |  | 1401-2294-177069 | 1401/05/23 | این مدرک بر اساس آخرین نسخه PMS به روز رسانی شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 5/21/2022 |  |  |  |  | Date: