## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DG-0001_D04 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1208 |  |  | Transmital Date: 7/30/2022
Document Title:Block Diagram Configuration For Control/ESD/F&G System - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1208 |  |  | Transmital Date: 7/30/2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0001_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به عدم اعمال اکثر نظرات این اموردر نامه 54898 مورخ 1401/2/19 مدرک عودت میگردد. از آنجایی که اکثر نظرات کارفرما به قوت خود باقی است لازم است کارشناسان ابزار دقیق پیملنکار برای جمع بندی سریعتر موضوع در هفته پیش رو در دفاتر کارفرما حضور پیدا کنند.( هماهنگی قبلی برای زمان و مکان جلسه و نیز حضور نمایندگان کارفرما انجام گردد) |  | 01/2294/238950 | 1401/07/06 | مطابق توافقات انجام شده ، موارد باقی مانده از نامه 54898 مورخ 1401/2/19 در مدرک اعمال شد. لازم به توضیح است با توجه به هماهنگی انجام شده توافق شد در صورت اعمال نظرات کارفرما مدرک بدون تشکیل جلسه به روز رسانی و ارسال گردد.
3
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 12 Sep 2022 |  |  |  |  | Date: