## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DT-0004_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1007 |  |  | Transmital Date: 25 May 2023
Document Title: Data Sheets For Pressure & Safety Relief Valves - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1007 |  |  | Transmital Date: 25 May 2023
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0004_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument Comments
1 | ليست مدارك مرجع در ديتا شيت اضافه گردد. |  | BK-SUR-ENG-INS-01-04627 | 2022-06-09 | مدارک مرجع در قسمت reference دیتاشیت آورده شده است.
2 | در قسمت PURCHASE عبارت will be finalized later اضافه گردد. |  | BK-SUR-ENG-INS-01-04627 | 2022-06-09 | اعمال گردید.
3 | متريال spring مطابق با مدرك specification for PSV در نظر گرفته شود. |  | BK-SUR-ENG-INS-01-04627 | 2022-06-09 | متریال spring مطابق با متریال بادی Carbon Steel می باشد که در دیتاشیت آورده شده است.
4 | با توجه به مغايرت بين اطلاعات خط در P&ID و ديتاشيت، اطلاعات مربوط به متريال بر اساس آخرين مستندات مجددا مورد بازنگري قرار گيرد. |  | BK-SUR-ENG-INS-01-04627 | 2022-06-09 | متریال براساس آخرین PMS و SPECIFICATION می باشد.
5 | تست ها مانند Hydro test و seat leakage test در نظر گرفته شود. |  | BK-SUR-ENG-INS-01-04627 | 2022-06-09 | آیتم 55 و 56 دیتاشیت مربوط به hydro test و seat leakage test می باشد.
Process Comments
6 | با توجه به وجود نقطه نظرات اساسي بر مدرك محاسبات شيرهاي ايمني بخش فرآيند، اين مدرك به لحاظ فرآيندي تا رسيدن به حداقل كيفيت مدرك پيشنياز (محاسبات شيرهاي ايمني) قابل بررسي نمي باشد. |  |  | 2022-05-31 | این مدرک با گروه پروسس idc گردید و آخرین نقطه نظرات پروسس بر روی این مدرک اعمال گردید.
Piping Comments
7 | نقطه نظرات پايپينگ در فايل پيوست آمده است. |  | BK-SUR-ENG-INS-01-04627 | 2022-06-09 | 1. شماره خط اصلاح گردید. 2. تغییر سایز redcucer در P&ID اعمال می گردد. 3. nace اعمال شد.
1
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 8 Jun 2022 |  |  |  |  | Date: