## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W008N-PEDCO-110-IN-MR-0002_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1232 |  |  | Transmital Date: 01 Aug 2022
Document Title: PMR For ControlSystem/Console/Furniture - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1232 |  |  | Transmital Date: 01 Aug 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | درجدول شماره 6 قسمت مربوط به Subject Of Supply ، به تجهیزات و متعلقات جانبی جهت ارتباط با بقیه سیستمها و پانلهای کنترل ازجمله ESD و F&G اشاره گردد. |  | 01/2294/216182 | 1401/06/17 | کلیه تجهیزات واسط در PMR مربوط به سیستم کنترل آورده میشود. NOTE اضافه شد.
2 | قسمتی از مدرک به آموزش درکارخانه سازنده و سایت همراه با توضیحات مربوطه اختصلص یابد. |  | 01/2294/216182 | 1401/06/17 | مدرک مطابق فرمت یکسان برای PMR های پروژه تهیه شده است. بخش مربوط به Training در SPEC به تفصیل آورده شده است. رجوع به SPEC در این مورد اضافه شد.
3 | صفحه 12 قسمت 11، عبارت Other Fee( if any) حذف گردد. |  | 01/2294/216182 | 1401/06/17 | مطابق خواست کارفرمای محترم اعمال شد.
4 | عبارات Ifany و If required از مدرک حذف گردد. |  | 01/2294/216182 | 1401/06/17 | مطابق خواست کارفرمای محترم اعمال شد.
5 | آخرین ویرایش مدارک تایید شده در پیوست PMR قرار گیرد |  | 01/2294/216182 | 1401/06/17 | مطابق خواست کارفرمای محترم اعمال شد.
6 | بدیهی است که مسئولیت تطابق مدارک اصلاحی با نقطه نظرات کارفرما و همچنین صحت و کفایت محتوای کلیه مدارک ارسالی مطابق شرح خدمات و استاندارد های تصریح شده در اسناد مناقصه استانداردهای IPS و دیگر مدارک پروژه بر عهده پیمانکار بوده و نقطه نظرات کارفرما رافع مسئولیت پیمانکار نمیباشد. |  | 01/2294/216182 | 1401/06/17 | ملاحظه شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 20 Aug 2022 |  |  |  |  | Date: