## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-MT-0005_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1123 |  |  | Transmital Date: 27/June/2022
Document Title: MTO For Gaskets |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0104-PI-TR-1123 |  |  | Transmital Date: 27/June/2022
[5 empty] | CRS No: BK-GCS-PEDCO-120-PI-MT-0005_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | فرمت توليد مدرك بايستي مطابق با مدارك ديگر رعايت شود بخشهاي عمومي مدرك از جمله Introductio و General Definition و Scope و Normative Reference در مدرك نوشته شود. |  | BK-SUR-ENG-PIP-01-05189 | 2022-07-17 | احتراما از انجاییکه مدرک MTO صرفا جهت اطلاع از مقدار تقریبی اقلام می باشد و از انجاییکه این مدک به تنهایی به سازندگان مربوطه ارسال نمی گردد و همیشه بخشی از مدرک MR می باشد لذا افزودن موارد مذکور مانند Introduction و General Definition و ...موضوعیت ندارد
2 | با توجه به اينكه MTO از خروجي مدل PDMS گرفته مي شود و هنوز مدل PDMS و PMS پروژه نهايي نشده است و نظر به اينكه اين مدرك بصورت IFI مي باشد لذا مسئوليت خريد متريال از نظر تعداد و مشخصات بعهده پيمانكار مي باشد. |  | BK-SUR-ENG-PIP-01-05189 | 2022-07-17 | احتراما به اطلاع می رساند در این برهه زمانی مدارک مذکور مانند PMS و ... نهایی گردیده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.Mousazadeh | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 09/07/2021 |  |  |  |  | Date: 09/07/2021