## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1195 |  |  | Transmital Date: 7/26/2022
Document Title: Process Data Sheets For 1st Stage G.C. Suction Drums |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1195 |  |  | Transmital Date: 7/26/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در سايزينگ اين تفكيكگر فرض بر وجود Vane pack شده است كه در اين مدرك لحاظ نشده است. اين عدم تطابق يا در اين مدرك يا در مدرك محاسبات مي بايست تصحيح گردد. |  | BK-SUR-ENG-PCS-01-05410 | 2022-08-13 | اعمال گردیده است .
2 | سايز نازل ورودي با محاسبات ارائه شده تطابق ندارد. |  | BK-SUR-ENG-PCS-01-05410 | 2022-08-13 | در محاسبات صورت گرفته سایز نازل ورودی 6 اینچ بدست آمده است، اما با توجه به سایز خط ورودی به تفکیکگر،نازل 8 اینچ در نظر گرفته شده است.
3 | نهايي سازي سايز نازل PSV پس از ارائه محاسبات تاييد شده نهايي سازي مي گردد. |  | BK-SUR-ENG-PCS-01-05410 | 2022-08-13 | مورد تایید است.
4 | در شماتيك قطره گير از تجهيزات توزيع جريان در نازل ورودي استفاده شده در حاليكه در محل مورد نظر در مدرك اين مطلب گنجانده نشده است. |  | BK-SUR-ENG-PCS-01-05410 | 2022-08-13 | در شماتیک طرح Internal reinforcement plate نشان داده شده که در لیست تجهیزات نیز گنجانده شده است.
5 | نقطه نظرات ارائه شده در سايزينگ ظروف، در اين مدرك نيز اعمال گردد. |  | BK-SUR-ENG-PCS-01-05410 | 2022-08-13 | اعمال می گردد.
6 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-05410 | 2022-08-13 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Faramarzpour | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: