## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PL-CN-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1326 |  |  | Transmital Date: 28/AUG/2022
Document Title: Pipeline Wall Thickness Calculation |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1326 |  |  | Transmital Date: 28/AUG/2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-CN-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به جلسه مورخ 1401/05/12 (سوابق) ضروریست در جداول هر سه مدرک حد مجاز خوردگی جدید حاصل شده که در Note 1 مدرک مطالعات خوردگی و انتخاب مواد به آن اشاره شده ذکر شود. پس از اصلاح جداول در خصوص سایر مدارک بررسی و اظهار نظر خواهد شد. |  | 1401/410/233388 | 1401/06/30 | - نقطه نظر کارفرمای محترم اعمال میگردد. .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 09/06/2022 |  |  |  |  | Date: 09/06/2022