## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DT-0006_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1348 |  |  | Transmital Date: 3 Sep 2022
Document Title: Data Sheets For Control/Regulator valves - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1084 |  |  | Transmital Date: 3 Sep 2022
[5 empty] | CRS No:NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0006_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پیرو نامه شماره 194443 مورخ 03/06/1401 با توجه به عدم انتخاب مناسب سایز کنترل ولو ها مطابق استاندارد IPS مدرک عودتداده میشود. |  | 01/2294/249326 | 1401/07/12 | مطابق توافقات انجام شده تعیین سایز شیر های کنترلی بر اساس محاسبات سازندگان و با توجه به الزامات ذکر شده دراستاندارد IPS تعیین خواهد شد. موارد در مدرک اعمال گردید. در رابطه با نامه شماره 194443 مطابق IPS-E-IN-160 الزام عدم تعیین سایز شیرکمترازنصف سایزخط رعایت خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 18 Sep 2022 |  |  |  |  | Date: