## Page 1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PI-RT-0001-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1327 |  |  | Transmital Date: 28/AUG/2022
Document Title: Piping Corrosion Study & Material Selection Report |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1327 |  |  | Transmital Date: 28/AUG/2022
[5 empty] | CRS No:PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-RT-0001-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | - در خصوص حد مجاز خوردگی برای بخش تسهیلات سرچاهی نقطه نظر دیگری مطرح نمی باشد. |  | 01/2294/240496 | 1401/07/07 | -
2 | - مبنای انتخاب 3 میلی متر حد مجاز خوردگی برای بخش منیفولد مشخص گردد. در نتایج ارائه شده خوردگی حفره ای با ریسک بالا برای این بخش پیش بینی شده است. با توجه به وجود نقاط مرده در بخش منیفولد، تمهیدات پیش بینی شده برای این بخش از سامانه لوله کشی مشخص گردد. |  | 01/2294/240496 | 1401/07/07 | - با توجه به اینکه پروژه مذکور به صورت Extension منیفولد موجود با حد مجاز خوردگی 3 میلی متر می باشد، در نظر گیری حد مجاز بالاتر منطقی نیست. لذا استفاده از ضخامت سنجی دوره ای ادوات پایش خوردگی کوپن و پروب منطقی تر می باشد.
3 | - در بخش 6.4 مدرک موضوع پایش خوردگی به صورت کلی بررسی شده ولی گزینه های نهایی و عملی در این پروژه مشخص نشده است. با توجه هب آب همراه پیش بینی شده به میزان 40 درصد ضروریست روشهای پایش خوردگی ازجمله ضخامت سنجی دوره ای، نصب کوپن و پروب و غیره در مدرک مشخص گردند. |  | 01/2294/240496 | 1401/07/07 | - نقطه نظر کارفرمای محترم اعمال می گردد.
4 | - لزوم اخذ و ارائه ی تاییدیه بهداشتی برای لوله با جنس پلی اتیلن با کاربرد آب آشامیدنی در مدرک ذکر گردد. |  | 01/2294/240496 | 1401/07/07 | - نقطه نظر کارفرمای محترم اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 09/06/2022 |  |  |  |  | Date: 09/06/2022