## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-PI-DG-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0932 |  |  | Transmital Date:5/11/2022
Document Title: Material Flow Diagram - W007S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-0932 |  |  | Transmital Date:5/11/2022
[5 empty] | CRS No:PEDCO-CRS-BK-W007S-PEDCO-110-PI-DG-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به نامه ی شماره BK-PEDCO-NISOC-0102-PI-LT-3673 مورخ 1401/02/21 (شماره وصول 3936) موارد به شرح ذیل به اطلاع می رساند: - اظهار نظر در خصوص این مدارک پس از نهایی شدن مدرک مطالعات خوردگی و انتخاب مواد و جنس و حد خوردگی امکانپذیر می باشد. - نقشه تسهیلات سرچاهی به پیوست ارسال می گردد. BK-W007S-PEDCO-110-PI-DG-0001_D00-Material Flow Diagram• W007S BK-W008N-PEDCO-110-PI-DG-0001_D00-Material Flow Diagram• W008N BK-W018S-PEDCO-110-PI-DG-0001_D00-Material Flow Diagram• W018S BK-W028-PEDCO-110-PI-DG-0001_D00-Material Flow Diagram• W028 BK-W035-PEDCO-110-PI-DG-0001_D00-Material Flow Diagram• W035 BK-W046S-PEDCO-110-PI-DG-0001_D00-Material Flow Diagram• W046S |  | 1401-2294-122170 | 1401/04/07 | مدارک مربوطه برای کارفرما ارسال شده است. لازم به ذکر است تسهیلات سرچاهی بر اساس نقشه های طراحی پایه و نقشه شماتیک به شماره S5L9002_001A ارسالی آن کارفرمای محترم در نظر گرفته شده است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 21-Nov-2021 |  |  |  |  | Date: 21-Nov-2021