## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1195 |  |  | Transmital Date: 7/26/2022
Document Title: Process Data Sheets For Inlet Gas K.O. Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1195 |  |  | Transmital Date: 7/26/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در داده برگ فرآیندی (Inlet K.O Drum) V-2105 در مورد نازل های L1 و L2 مطابق با توصیه شماره 33 در Appendix D مدرک "HAZOP Rreport For Compressor Station " می باید عمل شود. همچنین دلیل حذف نازل های L7 و L8 (Level Transmiter) مربوط به LIT-2118 برای این تجهیز بیان گردد. |  | 1401-2294-219178 | 1401/06/20 | مطابق با توصیه شماره 33 در Appendix D مدرک "HAZOP Rreport For Compressor Station " نازل L1 روی مخزن و نازل L2 رویBOOT مربوط به STAND PIPE LIT-2119و LG-2116 در نظر گرفته شده است. نازلهای مربوط به LIT-2118 حذف نشده و شماره انها به L5/L6 تغییر یافته است.
2 | Liquid Level های مندرج برای Boot مربوط به V-2105 در شماتیک با آخرین P&ID مطابقت ندارد و باید اصلاح گردد. همچنین در محاسبات سایزینگ تجهیز مذکور، اطلاعاتی در این خصوص ارایه نشده است. |  | 1401-2294-219178 | 1401/06/20 | LEVEL های روی BOOT مخزن مطابق با توافقات جلسات HAZOPدر نظر گرفته شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: