## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0013 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1196 |  |  | Transmital Date:7/26/2022
Document Title: Process Data Sheets For Fuel Gas K.O. Drum |  |  |  |  | PEDCO Tr. No.BK-PEDCO-NISOC-0005-PR-TRT-1196 |  |  | Transmital Date:7/26/2022
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-PR-DT-0013-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | محل اتصال نازل L4(Level Transmiter) برای V-2205( Fuel Gas K.O Drum) می باید مورد بازنگری قرار گیرد. همچنین HHLL و LLL مندرج در شماتیک مطابق با آخرین PID اصلاح گردد. |  | 1401-2294-219332 | 1401/06/20 | اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Faramarzpour | Signature |  |  |  | Clarified By: M.Aryafar | Signature
| Date: |  |  |  |  | Date: