## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0013 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1196 |  |  | Transmital Date:7/26/2022
Document Title: Process Data Sheets For Fuel Gas K.O. Drum |  |  |  |  | PEDCO Tr. No.BK-PEDCO-NISOC-0005-PR-TRT-1196 |  |  | Transmital Date:7/26/2022
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-PR-DT-0013-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پیشنهاد می گردد ابعاد مخزن به صورت 450mm X 2950mm در نظر گرفته شود و این مورد در سایر مدارک مرتبط نیز اصلاح گردد. |  | BK-SUR-ENG-PCS-01-05441 | 2022-08-14 | ابعاد مخزن به صورت 438mm X 2950mm بر اساس مدرک محاسبات Drum Sizing در نظر گرفته شده است.
2 | ارتفاع ظرف با عدد مندرج در مدرک P&ID مغایرت دارد. |  | BK-SUR-ENG-PCS-01-05441 | 2022-08-14 | اصلاح گردید.
3 | کلیه سطوح فرآیندی ظرف در مدرک دیتاشیت درج گردد. |  | BK-SUR-ENG-PCS-01-05441 | 2022-08-14 | اعمال گردید.
4 | ضروريست نقطه نظرات ذينفع اصلي در خصوص مدرك مذكور اعمال گردد. |  | BK-SUR-ENG-PCS-01-05441 | 2022-08-14 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: