## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-MR-0005_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1127 |  |  | Transmital Date: 28 Jun 2022
Document Title: PMR For Control Valves - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1127 |  |  | Transmital Date: 28 Jun 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0005_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص مورد دو Reply Sheet ، پیرو نامه 194443 مورخ 1401/06/03 و بحث های مطرح شده در جلسات P&ID و HAZOP سایز کنترل ولوها مورد بازنگری قرار گیرد.( مطابق استاندارد IPS سایز کنترل ولو تا یک سایز پایین تر از خط می تواند در نظر گرفته شود.) |  | 01/2294/205792 | 1401/06/10 | مطابق توافقات انجام شده تعیین سایز شیر های کنترلی بر اساس محاسبات سازندگان و با توجه به الزامات ذکر شده دراستاندارد IPS تعیین خواهد شد. موارد در مدرک اعمال گردید. مطابق IPS-E-IN-160 الزام عدم تعیین سایز شیرکمترازنصف سایزخط رعایت خواهد شد.
2 | در خصوص دیگر موارد REPLY Sheet نظر خاصی مطرح نمیباشد. |  | 01/2294/205792 | 1401/06/10 | -
3 | بدیهی است که مسئولیت تطابق مدارک اصلاحی با نقطه نظرات کارفرما و همچنین صحت و کفایت محتوای کلیه مدارک ارسالی مطابق شرح خدمات و استاندارد های تصریح شده در اسناد مناقصه استانداردهای IPS و دیگر مدارک پروژه بر عهده پیمانکار بوده و نقطه نظرات کارفرما رافع مسئولیت پیمانکار نمیباشد. |  | 01/2294/205792 | 1401/06/10 | ملاحظه شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 31 Jul 2022 |  |  |  |  | Date: