## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-DT-0005_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1015 |  |  | Transmital Date: 28 May 2022
Document Title: Data Sheets For Pressure & Safety Relief Valves |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1015 |  |  | Transmital Date: 28 May 2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0005_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اينكه مدارك پيش نياز مانند P&ID، Spec و Creiteria نهايي نيست هر گونه تغيير در مدارك مذكور بايد در اين مدرك نيز منعكس گردد. |  | BK-SUR-ENG-INS-01-04679 | 2022-06-11 | ملاحظه و بررسی می گردد.
2 | براي PSV-3201، outlet connection تناقض با ديتاهاي P&ID دارد. |  | BK-SUR-ENG-INS-01-04679 | 2022-06-11 | outlet connection مطابق با p&id می باشد.
3 | اطلاعات فرآيندي بر اساس آخرين PFD و P&ID نهايي گردد. |  | BK-SUR-ENG-INS-01-04679 | 2022-06-11 | این مدرک با گروه پروسس idc گردید و آخرین نقطه نظرات پروسس بر روی این مدرک اعمال گردید.
4 | نقطه نظرات بخش پايپينگ به پيوست آمده است. |  | BK-SUR-ENG-INS-01-04679 | 2022-06-11 | ملاحظه و بررسی می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 11 Jun 2022 |  |  |  |  | Date: