## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-PL-MT-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0058 |  |  | Transmital Date:22-Aug-2021
Document Title: MTO For Line Pipes (Flow lines) - W007S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0012-PL-TR-0058 |  |  | Transmital Date:22-Aug-2021
[5 empty] | CRS No:CRS-BK-W007S-PEDCO-110-PL-MT-0001-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اينكه مدرك بر اساس مدارك مهندسي پايه تهيه گرديده است در این برهه نقطه نظر خاصی مطرح نیست. البته مدارك Pipeline Material Specification و Pipeline Wall Thickness Calculation بايستي ارائه گردد و تأييد نهايي مدرك منوط به ارائه مدارك فوق و نقشه Plan & Profile خط لوله مربوطه مي باشد. همچنين، بهتر است جهت خريد لوله حداقل 5 درصد Contingency در نظر گرفته شود. پیشبرد گام بعدی مهندسی بلامانع است. شایان ذکر است مسئولیت هر نوع نقص و یا کمبود در مدرک و مترا‍ژ لوله برآورد شده به عهده پیمانکار است. |  | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | تمامی مدارک پیش نیاز براساس صورتجلسه مورخ 1401/05/12 نهایی گردیده و قبلا طی ترنسمیتال 1326 ارسال گردیده اند.
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 22-Aug-2021 |  |  |  |  | Date : 22-Aug-2021