## QAQC
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No. : BK-W018S-PEDCO-110-PL-MR-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0299 |  |  |  | Transmital Date: 12/6/2021
Document Title: PMR For Line Pipes - W018S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PL-TR0299 |  |  |  | Transmital Date: 12/6/2021
[5 empty] | CRS No: CRS-BK-W018S-PEDCO-110-PL-MR-0001_D00 |  |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Brief Action | Client Conclusion
1 | در بند 5.1.1، عبارت QA Organization به QA/QC Organization Chart تغيير يابد. |  | BK-SUR-ENG-PPL-00-02321 | 15/12/2021 | اعمال گردید
2 | در بند 5.1.3 : 1. با توجه به الزامات قراردادي، گواهينامه 3.1به 3.2 تغيير يابد. 2.محتويات گواهينامه متريال ميبايست بر اساس حداقل نيازمنديهاي API 5L 46 Ed و IPS-M-PI-190-4 باشد. 3. API 5L 2012 به API 5L 46 Ed تغيير يابد. 4. عبارت "NACE MR0175/ISO 15156" به" الزامات Annex H استانداردهاي API5L 46 Ed و IPS-M-PI-190-4" تغيير يابد. 5..استاندارد BS EN10204 جايگزين استاندارد DIN 50049 شده است. لذا استاندارد DIN50049 حذف گردد. |  | BK-SUR-ENG-PPL-00-02321 | 15/12/2021 | اعمال گردید
3 | در بند 6: 1-عبارت "Project ITP Procedure" به "Commodity Procurement and Manufacturing Inspection Instruction" به شماره مدرك ICE-EID-MI-SP01-Rev.01 تغيير يابد. 2-دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه گردد. |  | BK-SUR-ENG-PPL-00-02321 | 15/12/2021 | اعمال گردید
4 | در جدول Attachment 1(List of Reference/Applicable Documents) مدارك زير اضافه گردد: 1- Piping Material Specification 2- Specification for Transportation, Handling, Storage of Pipe 3- Specification For Color Coding and Marking 4- Final Data Book (FDB) Requirements 5-دستورالعمل بازرسي خريد و ساخت كالا به شماره ICE-EID-MI-SP01-Rev01 . 6-دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV01 . |  | BK-SUR-ENG-PPL-00-02321 | 15/12/2021 | اعمال گردید
5 | در جدول Attachments 2 (Vendor Documents Minimum Requirements): 1. مدارك مشخص شده در سر فصل هاي Quality, Manufacturing, Testing تجميع شده و در يك سر فصل تحت عنوان مدارك QA/QC آورده شود. 2. حداقل نيازمنديهاي مدارك بر اساس الزامات استاندارد API 5L 46ED, IPS-M-PI-190-4 بازنگري گردد. 3. در رديف 018، عبارت "Painting Procedure" به "Coating Procedure" تغيير يابد. 4- عبارت "List of Documents will be Finalized in VDLS" به عنوان نوت اضافه گردد |  | BK-SUR-ENG-PPL-00-02321 | 15/12/2021 | اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: A.Zandi/F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 15-Dec-2021 |  |  |  |  | Date: 15-Dec-2021