## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-CN-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1194 |  |  | Transmital Date: 7/26/2022
Document Title: CALCULATION NOTE FOR DRUM SIZING |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1194 |  |  | Transmital Date: 7/26/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | لازم است مبنای بیشینه مصارف دیزل (Max.Diesel Consumption) مندرج در جداول بخش 7 مدرک برای V-2206 A/B و زمان ماند (Hold-Up Time) در نظر گرفته شده برای هر کدام بیان گردد. |  | 1401-2294-219105 | 1401/06/20 | بنا به آخرین تصمیمات اتخاذ شده ابعاد تانک دیزل برابر با ابعاد محاسباتی مطالعات مقدماتی در نظر گرفته شده است. مبنای بیشینه ی مصارف در بند 4.3 مدرک Utilility Consumption بیان گردیده است، همچنین محاسبات مربوط به زمان ماند بیشینه ی مصارف بر اساس ظرفیت عملیاتی مخزن گزارش گردیده است.
2 | بیشینه مصارف قید شده برای دیزل در مدرک مطابق با محاسبات ضمیمه (فایل اکسل محاسباتی) نمی باشد.لازم به ذکر است که محاسبات فایل ضمیمه شده منطقی است. |  | 1401-2294-219105 | 1401/06/20 | بنا به آخرین تصمیمات اتخاذ شده ابعاد تانک دیزل برابر با ابعاد محاسباتی مطالعات مقدماتی در نظر گرفته شده است و تغییرات لازم در مدرک اعمال گردیده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: