## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W018S-PEDCO-110-PI-MR-0007_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0613 |  |  | Transmital Date: 2/20/2022
Document Title: PMR For Sampling Connection Set - W018S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-0613 |  |  | Transmital Date: 2/20/2022
[5 empty] | CRS No: CRS-BK-W018S-PEDCO-110-PI-MR-0007_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بند 5.1.1، عبارت "QA Organization" به "QA/QC Organization Chart" تغيير يابد. |  | BK-SUR-ENG-PIP-00-03420 | 08.03.2022 | اعمال گردید
2 | در بند 6: 1-عبارت "Project ITP Procedure" به "دستورالعمل بازرسي خريد و ساخت كالا" تغيير يابد. 2-دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه گردد. |  | BK-SUR-ENG-PIP-00-03420 | 08.03.2022 | اعمال گردید دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 در لیست مدارک پیوست اضافه گردید.
3 | در جدول Attachment 1(List of Reference/Applicable Documents): 1- Piping Material Specification 2- Specification For Transportation,Handling,Storage of Pipes and other materials 3-دستورالعمل FDB Requirements اضافه گردد. 4-دستورالعمل Packing, Marking, Transportation Procedure اضافه گردد. |  | BK-SUR-ENG-PIP-00-03420 | 08.03.2022 | اعمال گردید
4 | در جدول Attachments 2 (Vendor Documents Minimum Requirements): 1. در رديف 1، عبارت "See Attachmen 2" حذف گردد. 2. عبارت "List of Documents will be Finalized in Vendor Document Index and Schedule" به عنوان نوت اضافه گردد. |  | BK-SUR-ENG-PIP-00-03420 | 08.03.2022 | اعمال گردید
5 | در بند 5.1.3، گواهينامه متريال بايد Type 3.2 باشد. |  | BK-SUR-ENG-PIP-00-03420 | 08.03.2022 | اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman J.Mosazadeh | Signature |  |  |  | Clarified By: A.Dabiri | Signature | M.Fakharian
| Date:23/02/2022 |  |  |  |  | Date:23/02/2022