## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-LI-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1283 |  |  | Transmital Date: 8/17/2022
Document Title: Tie in List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1283 |  |  | Transmital Date: 8/17/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0003_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | تعداد و مشخصات نقاط اتصال مطابق بازديد مورخ 8-6-1401 بروزرساني گردد. |  | BK-SUR-ENG-PCS-01-05604 | 2022-09-05 | اعمال گردید.
2 | مشخصات نقطه اتصال به خط لوله گلخاري در صورت تغيير توسط ذينفع اصلي در مدرك بروزرساني گردد. |  | BK-SUR-ENG-PCS-01-05604 | 2022-09-05 | اعمال گردید.
3 | نقاط اتصال به رينگ آب آتشنشاني موجود در اين مدرك گنجانده شود. |  | BK-SUR-ENG-PCS-01-05604 | 2022-09-05 | این نقطه اتصال با Ti-in 2109 در مدرک ذکر گردیده است.
4 | تمامي فشار هاي طراحي در ويرايش بعدي مي بايست مشخص گردد. |  | BK-SUR-ENG-PCS-01-05604 | 2022-09-05 | فشارهای طراحی در مدرک قید گردیده است در ارتباط با خط ورودی از بینک پس از دریافت اطلاعات نهایی از کارفما در مدرک گنچانده خواهد شد.
5 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-05604 | 2022-09-05 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Faramarzpour | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: