## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0277 |  |  | Transmital Date: 28/NOV/2021
Document Title: PMR For Gas Compressor Package |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0009-ME-TR-0277 |  |  | Transmital Date: 28/NOV/2021
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0001_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
| Please add a note , TANDEM compressor is not acceptable, if vendor is willing to offer , it shall receive the End-user's technical approval |  | BK-SUR-ENG-MEC-00-02300 | 2021-12-15 | Noted, this comment already mentioned in data sheet.
| Cooling water system shall be clearly mentioned plan D , so the doubel heat exchanger shall be considered. |  | BK-SUR-ENG-MEC-00-02300 | 2021-12-15 | Air cooled water cooler has been considered for cooling water system.
| List of Spare part shall be submitted for review and to be attached MR. Gaurantee section shall be added |  | BK-SUR-ENG-MEC-00-02300 | 2021-12-15 | Noted
| In scope of supply : Skid shall be as per API686 , Mounting plate and sole plate shall be considered Lubrication system as per API614 shall be mentioned PLC logic shall be mentioned is by vendor UCP is necessary , please revmove if required |  | BK-SUR-ENG-MEC-00-02300 | 2021-12-15 | 1. Please specify the project reference for this comment. 2. Noted, already specified in compressor spec. 3. Noted, already specfied in MR. 4. Noted, but the item which is specified as " if required " is UPS not UCP.
| Certifications as following shall be supplied by Vendor Material Certification (for pressure parts) • Material Certification (for Non Pressure parts) • Hazardous Area certification for electrical items |  | BK-SUR-ENG-MEC-00-02300 | 2021-12-15 | Noted
1 | Rev of each reference docments which have been mentioned in MR shall be specified Please clarify if ITP for recirocating compressor are included in ITP for equipment or not?, if so, please ignore the comment,otherwise the ITP for reciprocating shall be issued. Reference documents of each dicipline shall be separated and specified in one catergory |  | BK-SUR-ENG-MEC-00-02300 | 2021-12-15 | Noted
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.BAVARSAD | Signature | H.naserizadeh |  |  | Clarified By: H. Adineh | Signature | M.Fakharian
| Date:12/15/2021 |  |  |  |  | 2022-01-04

## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0011_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1227 |  |  | Transmital Date: 31/Jul/2022
Document Title: PMR For Fire Water Pumps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-ME-TR-1227 |  |  | Transmital Date: 31/Jul/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0011_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در نامه شماره 00/2294/438865 بیان گردید مدارک MR پس از تولید و نهایی شدن کلیه مدارک مهندسی تفصیلی مربوطه می بایست تولید گردد، چرا که تمامی مدارک در مورد هر پکیج خرید می بایست با درج آخرین ویرایش نهایی و عنوان آن در متن ضمیمه MRها شوند. |  | 00/2294/213921 | 1401/06/15 | مدرک MR پمپ های آتش نشانی به همراه آخرین ویرایش مدارک مرجع (ATTACHMENT#1) خدمت کارفرمای محترم ارسال می گردد. خواهشمند است جهت تسریع در امور خرید بررسی مدرک مذکور در دستور کار آن کارفرمای محترم قرار گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date:27/02/2022 |  |  |  |  | 2022-10-22