## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-IN-DC-0002_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0968 |  |  | Transmital Date: 17 May 2022
Document Title: Instrument & Control System Design Criteria |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-0968 |  |  | Transmital Date: 17 May 2022
[5 empty] | CRS No: NISCO-CRS-BK-SSGRL-PEDCO-110-IN-DC-0002_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص مورد17، مطابق نظرات این امور بر مدرک Control System Block Diagram Configuration اصلاح لازم متناسب با واحد کلاستر بینک صورت گیرد. |  | 01/2294/164856 | 1401/05/11 | کامنت کارفرمای محترم در مورد 17 شفاف نمی باشد ولی این مدرک و Control System Block Diagram Configuration متناظر گردید.
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 31 May 2022 |  |  |  |  | Date: