## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-EL-DW-0004-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0280 |  |  | Transmital Date: 28-Nov-2021
Document Title: Typical Installation Details & Notes For Power System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0009-EL-TR-0280 |  |  | Transmital Date: 28-Nov-2021
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0004-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Re. item 1-5 above, it has not been shown and shall be added. |  | BK-SUR-ENG-ELE-00-01899 | 2021-11-03 | Implemented
2 | According to our telephone conversation, typical power installation details for transformers (Pages 22&23) shall be modified. (Incoming and outgoing cables, bus duct, …. Shall be shown.) |  | BK-SUR-ENG-ELE-00-01899 | 2021-11-03 | Implemented
3 | According to our telephone conversation, typical power installation details for diesel generator shall be modified. (Outgoing cables, Tray/Ladder, …. Shall be shown.) |  | BK-SUR-ENG-ELE-00-01899 | 2021-11-03 | Implemented
4 | The history of previous comments has been deleted by consultant so it is not possible to check document. |  | BK-SUR-ENG-ELE-00-02138 | 2021-11-29 | از این به بعد تاریخچه کامنت شیت ها در پاسخ این مشاور نگه داشته شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 29-Nov-21 |  |  |  |  | Date: