## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W035-PEDCO-110-IN-TB-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1012 |  |  | Transmital Date: 28 May 2022
Document Title: TBE/TBA For Field Instrumentations - W035 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1012 |  |  | Transmital Date: 28 May 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W035-PEDCO-110-IN-TB-0002_D00 |  |  | CRS Status: | C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-05635 | 2022-09-12 | ملاحظه گردید.
2 | تمامي TBE ها بايد يك فايل گزارش بصورت ورد داشته باشند كه با ادله كافي وندور مورد نظر را به ترتيب اولويت پيشنهاد دهند. |  | BK-SUR-ENG-INS-01-05635 | 2022-09-12 | مدرک مطابق با فرمت تایید شده TBE تهیه گردیده و به روز رسانی شده است.
3 | Deviation list براي تمامي سازنده ها و تامين كننده ها ارائه شود. |  | BK-SUR-ENG-INS-01-05635 | 2022-09-12 | Deviation List از تمامی سازندگان درخواست گردیده است. در صورت عدم ارائه این مورد در جدول TBE ذکر گردیده است.
4 | با توجه به اينكه مدرك Datasheet و spec نهايي نمي باشد موارد در صورت تغيير به وندور اطلاع رساني گردد. |  | BK-SUR-ENG-INS-01-05635 | 2022-09-12 | ملاحظه گردید.
5 | اين نكته در نظر داشته باشد كه مطابق قرارداد تمامي وندور ها بايد در ليست AVL قرار داشته باشند. |  | BK-SUR-ENG-INS-01-05635 | 2022-09-12 | ملاحظه گردید.
6 | با توجه به مذاكرات انجام شده، نامه هاي ارسال شده، در اين مدرك و همچنين نقطه نظرات كارفرما، تمامي موارد در خصوص انتخاب وندور و انتخاب تجهيز در نظر گرفته شود. مستندات به پيوست آمده است. |  | BK-SUR-ENG-INS-01-05635 | 2022-09-12 | ملاحظه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 12 Sep 2022 |  |  |  |  | Date: