## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-EL-DW-0003-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0182 |  |  | Transmital Date: 25-Oct-2021
Document Title: Typical Installation Details & Notes For Lighting System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0008-EL-TR-0182 |  |  | Transmital Date: 25-Oct-2021
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0003-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Installtion detail for following items shall be added: |  | BK-SUR-ENG-ELE-00-01447 | 2021-09-01
1-1 | Installation detail for recessed fluorescent lamp 600X600mm |  | BK-SUR-ENG-ELE-00-01447 | 2021-09-01 | اعمال گردید. |  |  | Noted&Closed.
1-2 | Installation detail for fluorescent & incandescent for celling mounted and exit sign lighting |  | BK-SUR-ENG-ELE-00-01447 | 2021-09-01 | از آنجا که دیگر چراغ رشته ای کاربردی ندارد اعمال نگردید همچنین چراغ EXIT هم نمایش داه شده است. |  |  | See item 3 below.
1-3 | Installation detail for Switch and socket flush/surface mounted. |  | BK-SUR-ENG-ELE-00-01447 | 2021-09-01 | اعمال گردید. |  |  | Noted&Closed.
1-4 | Installation detail for bulk head lighting fixture wall mounted. (Outdoor) |  | BK-SUR-ENG-ELE-00-01447 | 2021-09-01 | اعمال گردید. |  |  | See item 4 below.
1-5 | Installation detail for Fl. LTG. Fixture bracket mtd. Steel structure (non-hazardous & hazardous) |  | BK-SUR-ENG-ELE-00-01447 | 2021-09-01 | اعمال گردید. |  |  | See item 5 below.
2 | According to IPS drawing code numbering, Lighting installation detail (LID) number shall be be added and specified for each installtion details in the document. Meanwhile it shall be added to index sheet too. |  | BK-SUR-ENG-ELE-00-01447 | 2021-09-01 | در قسمت رفرنس شماره مدرک روشنایی به شماره IPS-D-El-300 اضافه گردید. |  |  | Noted&Closed.
3 | Re. item 1-2 above, installation details for exit sign lighting shall be shown with details. (Surface or flush mounted, With or without JB, distance between door and exit sign, …) |  | BK-SUR-ENG-ELE-00-01899 | 2021-11-03 | با توجه به کاربرد کم آنها در مدارک این پروژه، فقط در نقشه های جانمایی تجهیزات (Layout) نشان داده شده است.
4 | Re. item 1-4 above, it shall be modified base on our telephone conversation. |  | BK-SUR-ENG-ELE-00-01899 | 2021-11-03
5 | Re. item 1-5 above, it has not been shown and shall be added. |  | BK-SUR-ENG-ELE-00-01899 | 2021-11-03
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 03-Nov-21 |  |  |  |  | Date: