## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-GE-RT-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-01150 |  |  | Transmital Date:07/13/2022
Document Title:Value Engineering Study Report |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-01150 |  |  | Transmital Date:07/13/2022
[5 empty] | CRS No: CRS-BK-PPL-PEDCO-320-GE-RT-0002_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1401-2294-165152 | 1401/05/12 | صورتجلسه مذکور در خصوص اخذ تاییدیه از واحد بازرسی آن کارفرمای محترم در خصوص کیفیت خط مزبور می باشدو اشاره ای به ظرفیت خط و تلمبه ها نگردیده است. علی ایحال به استحضار می رساند: • خط مورد نظر 4 اینچ می باشد که مطابق با مدارک پایه ، سایز در نظر گرفته شده برای ارسال مایعات نیز 4 اینچ است. • فلسفه جمع آوری مایعات واحد Closed Drain موجود و جدید و انتقال آن به Slug Catcher در داخل واحد جدید اتفاق خواهد افتاد و ربطی به سایزینگ پمپ و خط انتقال ندارد. • سایزینگ پمپ های انتقال کاندنسیت براساس فلسفه جدید قبلا طی ترنسمیتال 1179 به حضورتان ارسال گردیده است. ( با سایزینگ انجام شده تغییری در دبی مایعات ارسالی صورت نپذیرفته و تغییری در سایز خط لوله نیز مورد نیاز نمی باشد).
2 |  |  | 1401-2294-165152 | 1401/05/12 | سایز خط لوله انتقال گاز ترش از کلاستر بینک به ایستگاه تقویت فشار جدید بینک مطابق با شرح کار ( Snapshot ذیل) ، اسناد پایه 6 اینچ می باشد.سایز این خط در مدارک تفصیلی نیز 6 اینچ می باشد. لذا با توجه به مطالب فوق خواهشمند است موضوعات مجددا بررسی و درصورت رفع ابهامات اشاره شده فوق دستورفرمایید مراتب تایید این مدرک به این پیمانکار ابلاغ گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: G.Khosravizadegn/ F.Amiri/ | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 24-Jan-2022 |  |  |  |  | Date: 24-Jan-2022