## عمومی
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No. : BK-GNRAL-PEDCO-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PI-TT-0001 |  |  |  | Transmital Date: |  | 2021-07-07
Document Title: Master Document Identification List (MDL) |  |  |  |  | PEDCO Tr. No.: - |  |  |  | Transmital Date: -
[5 empty] | CRS No: BK-PEDCO-NISOC-CRS-0002 |  |  |  | CRS Status:
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No:BK-GNRAL-PEDEC-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1047 |  |  | Transmital Date: | 2022-06-07
Document Title: Master Document List (MDL) & Updating |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-GE-TR-1047 |  |  | Transmital Date: | 2022-06-07
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G06 |  |  | CRS Status: | AP
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Brief Action | Client Conclusion | Clarification (By EPC Contractor)
1 | پیرو نامه شماره 4294/2294/01 مورخ 1401/02/08 مقرر گردید، عناوین کلیه مدارک مرتبط با عبارت PABX با عبارت Telecomm. جایگزین گردد و وزن مدارک بدون تغییر باقی بماند. |  | 1401-2290-111800 | 2022-06-22 | اعمال گردید
2 | در خصوص سایر مدارک اعلام شده در لیست مدارک در حال حاضر نقطه نظر خاصی مطرح نمی باشد |  | 1401-2290-111800 | 2022-06-22 | -
3 | ضروری است فایل pms پروژه در بخش مهندسی سطح الارض منطبق بر آخرین MDR پروژه اصلاح و ارسال گردد. |  | 1401-2290-111800 | 2022-06-22 | پس از دریافت تاییدیه برروی لیست مدارک (MDL) پیوست تهیه و ارسال خواهد شد
4
5
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 07.Aug.2021