## ابزار دقیق
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No. : BK-GNRAL-PEDCO-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PI-TT-0001 |  |  |  | Transmital Date: |  | 2021-07-07
Document Title: Master Document Identification List (MDL) |  |  |  |  | PEDCO Tr. No.: - |  |  |  | Transmital Date: -
[5 empty] | CRS No: BK-PEDCO-NISOC-CRS-0002 |  |  |  | CRS Status:
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No:BK-GNRAL-PEDEC-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1047 |  |  | Transmital Date: | 2022-06-07
Document Title: Master Document List (MDL) & Updating |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-GE-TR-1047 |  |  | Transmital Date: | 2022-06-07
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G06 |  |  | CRS Status: | C
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Brief Action | Client Conclusion | Clarification (By EPC Contractor)
Instrument
1 | عطف به كامنت هاي ارسالي بر روي CRS ها، با توجه به شباهت عناوين مدارك، جهت تمايز بهتر مدارك لازم است علاوه بر شماره مدرك نام ناحيه در عنوان ذكر گردد. بعنوان مثال: Instrument design Criteria for Gas Compressor station o Instrument design Criteria for Extension of Binak B/C Manifold o instrument design Criteria for Pipeline 8" & 4 |  | س ط ب /10642 | 2022-07-20 | مطابق با صورتجلسه مربوطه نیازی به تغییر نام مدرک در این مقطع نمی باشد
2 | در مدارك بخش PIPE LINE 6” & 8” مدارك مربوط به سيستم كنترل و ESD بصورت مشترك ارائه شده است (براي مثال I/O ليست) ، اين درحاليست كه در رويژن هاي پيشين مدارك بصورت مجزا ارائه شده است و ارائه مدارك بصورت مشترك روال تاييد شده اي نمي باشد. |  | س ط ب /10642 | 2022-07-20 | مدرک ذکر شده با ویرایش D00 و با عنوان درج شده در MDL ارسال شده است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 07.Aug.2021

## مخابرات
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No. : BK-GNRAL-PEDCO-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PI-TT-0001 |  |  |  | Transmital Date: |  | 2021-07-07
Document Title: Master Document Identification List (MDL) |  |  |  |  | PEDCO Tr. No.: - |  |  |  | Transmital Date: -
[5 empty] | CRS No: BK-PEDCO-NISOC-CRS-0002 |  |  |  | CRS Status:
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No:BK-GNRAL-PEDEC-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1047 |  |  | Transmital Date: | 2022-06-07
Document Title: Master Document List (MDL) & Updating |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-GE-TR-1047 |  |  | Transmital Date: | 2022-06-07
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G06 |  |  | CRS Status: | C
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Brief Action | Client Conclusion | Clarification (By EPC Contractor)
Telecom
1 | پيرو بند 1 نامه شماره 100876/2294/01 مورخ 23/03/1401 ذينفع اصلي پروژه در خصوص پاسخ به ترانسميتال TR-1004، كليه مدارك تحت عنوان PABX ميبايست به Telecom Equipment تغيير نام يابند. پيشنهاد ميگردد نام گذاري كليه مدارك به شرح ذيل تغيير يابد: 1- Specification For PABX Telecom Equipment (Telephone System) 2- Datasheet For PABX Telecom Equipment (Telephone System) 3- Block Diagram For PABX Telecom Equipment (Telephone System) 4- Cable Schedule For PABX Telecom Equipment (Telephone System) 5- MTO For PABX Telecom Equipment (Telephone System) 6- PABX Telephone System · PMR For PABX Telecom Equipment (Telephone System) · TBE For PABX Telecom Equipment (Telephone System) |  | س ط ب /10642 | 2022-07-20 | اعمال گردید
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 07.Aug.2021

## برق
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No. : BK-GNRAL-PEDCO-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PI-TT-0001 |  |  |  | Transmital Date: |  | 2021-07-07
Document Title: Master Document Identification List (MDL) |  |  |  |  | PEDCO Tr. No.: - |  |  |  | Transmital Date: -
[5 empty] | CRS No: BK-PEDCO-NISOC-CRS-0002 |  |  |  | CRS Status:
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No:BK-GNRAL-PEDEC-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1047 |  |  | Transmital Date: | 2022-06-07
Document Title: Master Document List (MDL) & Updating |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-GE-TR-1047 |  |  | Transmital Date: | 2022-06-07
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G06 |  |  | CRS Status: | C
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Brief Action | Client Conclusion | Clarification (By EPC Contractor)
Electrical
1 | پيرو مذاكره تلفني با توجه به تفكيك محاسبات DC/AC UPS كلاستر بينك از سرچاهي ها و اضافه نمودن مدارك مربوط به DC/AC UPS كلاستر بينك در ليست مدارك، ضروري است تغييرات اعمال شده در شيت مربوط به Change Log ثبت گردد. |  | س ط ب /10642 | 2022-07-20 | مطابق با صورتجلسه مربوطه تغییرات در نظر گرفته شد
2 | پيرو مذاكرات تلفني قبلي با توجه به مشخص شدن عدم نياز سرچاهي ها به AC UPS لذا مدارك مربوط به آن از ليست مدارك پروژه حذف گردد. |  | س ط ب /10642 | 2022-07-20 | مطابق با صورتجلسه مربوطه تغییرات در نظر گرفته شد
3
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 07.Aug.2021

## عمومی
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No. : BK-GNRAL-PEDCO-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PI-TT-0001 |  |  |  | Transmital Date: |  | 2021-07-07
Document Title: Master Document Identification List (MDL) |  |  |  |  | PEDCO Tr. No.: - |  |  |  | Transmital Date: -
[5 empty] | CRS No: BK-PEDCO-NISOC-CRS-0002 |  |  |  | CRS Status:
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No:BK-GNRAL-PEDEC-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1047 |  |  | Transmital Date: | 2022-06-07
Document Title: Master Document List (MDL) & Updating |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-GE-TR-1047 |  |  | Transmital Date: | 2022-06-07
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G06 |  |  | CRS Status: | C
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Brief Action | Client Conclusion | Clarification (By EPC Contractor)
1 | - |  | س ط ب /10642 | 2022-07-20 | با توجه به تغییرات کلی به وجود آمده در لیست مدارک، اوزان پس از نهایی سازی و تهیه WBS مربوطه اعمال خواهد شد.
2
3
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 07.Aug.2021