## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0007_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0338 |  |  | Transmital Date: 13/DeC/2021
Document Title: Mechanical Data Sheets For Diesel Oil Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0010-ME-TR-0338 |  |  | Transmital Date: 13/DeC/2021
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-ME-DT-0007_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | معیار انتخاب فشار طراحی مشخص گردد. |  | 00/2294/329500 | 1400/09/30 | فشار طراحی بر اساس مدارک فرآیند مشخص شده است.
2 | فشار طراحی در مدرک مشخص گردد. |  | 00/2294/329500 | 1400/09/30 | مشخص گردید.
3 | موارد غیر ضروری از بخش یادداشتها حذف گردد به عنوان نمونه، کاربرد استندپایپ در این مخزن مشخص نمی باشد. |  | 00/2294/329500 | 1400/09/30 | نظر کارفرمای محترم اعمال گردید.
4 | منظور از Client در متن مدرک مشخص نمی باشد. |  | 00/2294/329500 | 1400/09/30 | مشخص گردید.
5 | میزان کالای یدکی مطابق با پیوست 11 کتابچه پیمان در نظر گرفته شود. |  | 00/2294/329500 | 1400/09/30 | نظر کارفرمای محترم اعمال گردید.
6 | با توجه به اینکه محاسبات طراحی ارسال نشده است، ملاک تعیین مشخصات طراحی(به عنوان نمونه ضخامت) چه بوده است. پیشنهاد می گردد تعیین اینگونه اطلاعات با هماهنگی سازنده صورت پذیرد. |  | 00/2294/329500 | 1400/09/30 | نظر کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.BAVARSAD | Signature | H.naserizadeh |  |  | Clarified By: H.Adineh | Signature | M.Fakharian
| Date: 01/03/2021 |  |  |  |  | Date: 10/30/2022