## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK12-PEDCO-110-GT-RT-0001 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1081 |  |  | Transmital Date:06/15/2022
Document Title: Geotechnical Investigation Report - BK12 |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-GT-TR-1081 |  |  | Transmital Date:06/15/2022
[5 empty] | CRS No:NISOC-CRS-BK-BK12-PEDCO-110-GT-RT-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1401-2294-123165 | 1401/04/08 | تعداد گمانه ها با توجه به بررسی و مطالعات صورتگرفته مشخص گردیده است و کفایت آن مورد تایید است.
2 |  |  | 1401-2294-123165 | 1401/04/08 | اين گزارش براساس شرايط و محدوديت‌هاي ذكر شده در آن مورد استفاده قرار می گيرد. مشاهدات و نتيجه گيريهاي شرح داده شده در اين گزارش بر اساس نتایج حاصل از مطالعات ژئوتکنیک پروژه و صرفاً بر مبناي محدوده خدمات و تعدادگمانه های ذكر شده تنظيم گردیده ‌اند
3 |  |  | 1401-2294-123165 | 1401/04/08 | درحریم و شعاع گمانه ها مسئولیت صحت نتایج با مشاور ژئوتکنیک می باشد.حداقل گمانه ، محل و تعداد مورد نیاز در پروزه توسط مشاور ژئوتکنیک مشخص و مسئولیت گزارش ساختگاه و محدوده تعیین شده با ایشان می باشد.فواصل و شعاع نقاط اکتشافی در ایستگاه ها 50 - 100 متر و در مسیر خطوط لوله 200 - 500 متر می باشد.
4 |  |  | 1401-2294-123165 | 1401/04/08 | مطالعات و گزارش هیدرولوژی در حال انجام می باشد که پس از تکمیل مشخصات خواسته شده ارائه می گردد.
5 |  |  | 1401-2294-123165 | 1401/04/08
6 |  |  | 1401-2294-123165 | 1401/04/08 | گزارش منابع قرضه و پارامترهای اساس و زیر اساس در بازبینی بعدی ارائه می گردد.
7 |  |  | 1401-2294-123165 | 1401/04/08
8 |  |  | 1401-2294-123165 | 1401/04/08
|  |  | 1401-2294-123165 | 1401/04/08
|  |  | 1401-2294-123165 | 1401/04/08
|  |  | 1401-2294-123165 | 1401/04/08
|  |  | 1401-2294-123165 | 1401/04/08
|  |  | 1401-2294-123165 | 1401/04/08
|  |  | 1401-2294-123165 | 1401/04/08
|  |  | 1401-2294-123165 | 1401/04/08
|  |  | 1401-2294-123165 | 1401/04/08
2
3
4
5
6
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: