## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-GT-RT-0001 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1081 |  |  | Transmital Date:06/15/2022
Document Title: Geotechnical Investigation Report - BK14 |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-GT-TR-1081 |  |  | Transmital Date:06/15/2022
[5 empty] | CRS No:NISOC-CRS-BK-BK12-PEDCO-110-GT-RT-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | هيچگونه گزارش اطلاعات مربوط به لاگ هاي زمين شناسي و نتايج آزمايشات و ... و پيوست هاي مندرج ارائه نشده است. عمده نقطه نظرات مطرح شده بر مدارك مشابه - ترانسميتال هاي قبلي به قوت خود باقي است |  | BK-SUR-ENG-CIV-01-04721 | 2022-06-15 | اطلاعات مربوط به لاگ های زمین شناسی و نتایج آژمایشات و پیوست و .... ارائه شد
2
2
3
4
5
6
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: