## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0006_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1258 |  |  | Transmital Date: 09/August/2022
Document Title: PMR For Instrument/Plant Air & Nitrogen Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0107-ME-TR-1258 |  |  | Transmital Date: 09/August/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0006_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدارک MR پس از تولید و نهایی شدن کلیه مدارک مهندسی تفصیلی مربوطه (مانند مشخصات فنی، داده برگ ها، PMS و MTO و ... ) می بایست تولید گردد، چرا که تمامی مدارک مذکور در مورد هر پکیج خرید، می بایست با درج ویرایش نهایی و عنوان آن در متن، ضمیمه Mrها شوند. از آنجایی که بسیاری از مدارک مهندسی مرتبط (که در پیوست1 مدرک نیز اشاره شده است) ویرایش اولیه بوده و یا تاکنون نهایی نشده اند، لذا تولید این مدارک در این مقطع مورد تایید نبوده و قابل بررسی نیز نمی باشد. |  | 01/2294/222891 | 1401/06/22 | با توجه به اینکه مدارک پیشنیاز تقریبا نهایی شده اند لذا خواهشمند است بررسی مدرک مربوطه در دستور کار آن کارفرمای محترم قرار گیرد. لازم به ذکر است که مدارک پیشنیاز Rev.up شده و خدمت کارفرمای محترم به پیوست این مدرک ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: |  |  |  |  | Date: 11/02/2022