## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0008_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1258 |  |  | Transmital Date: 09/August/2022
Document Title: PMR For Chemical Injection Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0107-ME-TR-1258 |  |  | Transmital Date: 09/August/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0008_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرك MR پس از توليد و نهايي شدن كليه مدارك مهندسي مربوطه مانند مشخصات فني،PMS،MTO و ... مي بايست توليد گردد،چرا كه تمامي مدارك مذكور در هر پكيچ خريد مي بايست با درج ويرايش نهايي و عنوان آن در متن،ضميمه MRها شوند از آنجايي كه بسياري از مدارك مهندسي مرتبط ويرايش اوليه بوده و يا تا كنون نهايي نشده است لذا بررسي اين مدرك در اين مقطع زماني امكان پذير نمي باشد. |  | BK-SUR-ENG-MEC-01-05916 | 2022-10-18 | با توجه به اینکه مدارک پیشنیاز تقریبا نهایی شده اند لذا خواهشمند است بررسی مدرک مربوطه در دستور کار قرار گیرد. لازم به ذکر است که مدارک پیشنیاز Rev.up شده و به پیوست این مدرک ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: 10/18/2022 |  |  |  |  | Date: 11/05/2022