## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W028-PEDCO-110-CV-PY-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1331 |  |  | Transmital Date: 8/28/2022
Document Title: Civil and Structural drawings -W028 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-1331 |  |  | Transmital Date: 8/28/2022
[5 empty] | CRS No: NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0002-D06 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در پاسخ بند 2 از Clafication (By EPC Contractor) در خصوص Burn Pit اعلام می‌گردد که نیاز فنی، احداث گودال خاکی و استاندارد بوده که بدیهی است، تبعات و موارد قراردادی، متعاقبا اعلام خواهد شد. |  | 1401-2290-258365 | 1401/07/19 | اعمال گردید.
2 | پیرو نامه شماره 300405 مورخ 1400/9/10 عرض جاده دسترسی گودال سوخت برابر با 5 متر در نظر گرفته شود. همچنین عرض مفید 6 متر برای Access Road مدنظر قرار گیرد. |  | 1401-2290-258365 | 1401/07/19 | اصلاح شد.
3 | در Notes نقشه قید گردد: The water pool in not Client Requirements |  | 1401-2290-258365 | 1401/07/19 | اعمال گردید.
4 | تعیین هرنوع روگذر از قبیل پل، کالورت و ... پس از دریافت گزارش نهایی ژئوتکنیک/Flood Control، قابل اظهار نظر خواهد بود.(به مکاتبات 216813 مورخ 1401/6/17 و 85269 مورخ 1401/3/10 مراجعه شود که تاکنون نهایی نشده اند.) |  | 1401-2290-258365 | 1401/07/19 | گزارش ژئوتکنیک صلاح شده ارسال می گردد
5 | اشکالات ترسیمی ذیل برطرف گردند: - در شیت 1 از 42، پیت درین خط لوله 12 اینچ مربوط به سلر حذف شده است. بازگردانده شود. - صفحه 5 از 42 برش های 1 و 2 اصلاح شوند. برای برش 2 شبکه آرماتور به صورت یکپارچه نمایش داده شود و لوله هادی در محل آرماتورها با خط چین ترسیم شود و بالعکس آن در برش 1 اعمال گردد. - برای پاشنه تمامی Concrete Block Walls با بتن کف، ماهیچه (ملاتی) ترسیم گردد. |  | 1401-2290-258365 | 1401/07/19 | اعمال گردید.
6 | تمامی اطلاعات مربوط به Total Volume Table در این مدرک حذف شوند. |  | 1401-2290-258365 | 1401/07/19 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: