## Sheet 1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-SA-CN-0003-D00 |  |  |  |  | EPC Contractor Tr. No : BK-HD-PEDCO-T-0986 |  |  | Transmital Date:22/MAY/2022
Document Title: Fire Water Hydraulic Calculation Note |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-SF-TR-0986 |  |  | Transmital Date:22/MAY/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-SA-CN-0003-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در صفحه 6 بخش 5.2، سرعت 3.5m/s بر اساس استاندارد ذکر گردد. |  | 1401-2294-177132 | 1401/05/23 | اصلاح گردید.
2 | در بخش attachment خروجی نرم افزار وجود ندارد. |  | 1401-2294-177132 | 1401/05/23 | خروجی نرم افزار به صورت report در فرمت PDF مدرک پیوست شده بود. خروجی PDFو نیز خروجی نرم افزار Pipenet در ویرایش جدید مدرک ضمیمه شده است لذا در صورت عدم دریافت فایل از بخش DCC پیگیری صورت گیرد.
3 | لازم است فایل Native نرم افزار جهت بررسی نیز به این امور ارسال شود. |  | 1401-2294-177132 | 1401/05/23 | خروجی PDFو نیز خروجی نرم افزار Pipenet در ویرایش جدید مدرک ضمیمه شده است.
4 | لازم است پس از نهایی شدن نقشه سیستم آب آتش نشانی، مدرک فوق بروز رسانی و مجددا جهت بررسی به این امور ارسال گردد. |  | 1401-2294-177132 | 1401/05/23 | مدرک بر اساس نقشه نهایی سیستم آب آتش نشانی بروز رسانی و اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: