## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0028_D04 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1520 |  |  | Transmital Date: 19/Oct/2022
Document Title: Mechanical Data Sheets For Fire Water Jockey Pumps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0108-ME-TR-1520 |  |  | Transmital Date: 19/Oct/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0028_D03 |  |  | CRS Status:
item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که پیش تر متذکر گردید زمانیکه مدرک در وضعیت نهایی AFC ارسال می گردد می بایست نسبت به ویرایش قبلی تغییرات عمده نداشته باشد لذا با توجه به تغییرات اساسی این مدرک ضروریست دلایل بروز تغییرات در قالب Reply sheet بیان گردد. |  | 01/2294/294099 | 1401/08/12 | به اطلاع کارفرمای محترم می رساند مدرک مکانیکال دیتاشیت پمپ های جوکی در ویرایش D03 با توجه به تغییرات مدرک محاسبات هیدرولیک پمپ های آتش نشانی اصلاح گردید. همچنین با توجه به اینکه نوت های اضافه شده در ویرایش D03 ضروری نبوده و توسط سازندگان رعایت می شود لذا در ویرایش جدید از مدرک حذف می گردند.
2 | کلاس فلنج نازل ورودی و خروجی پمپ اصلاح گردد. |  | 01/2294/294099 | 1401/08/12 | نقطه نظر کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: |  |  |  |  | Date: 11/06/2022