## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W018S-PEDCO-110-PI-TB-0002-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1287 |  |  | Transmital Date:20-Aug-2022
Document Title: TBE For Fitting- W018S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0105-PI-TR-1287 |  |  | Transmital Date:20-Aug-2022
[5 empty] | CRS No:PEDCO-CRS-BK-W018S-PEDCO-110-PI-TB-0002-D00 |  |  | CRS Status: | C4
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | تاییدیه سازنده در لیست بلند نفت تنها برای شرکت پترو صنعت عادل ارسال شده است که ضروری است برای دیگر سازندگان نیز ارسال گردد. |  | 01/2294/218268 | 1401/06/19 | احتراما در ویرایش D01 مدرک گنجانده شده است.
2 | در مدارک ارسالی مشخص نشده است کالا ساخته خواهد شد و یا از انبار سازنده/تامین کننده تهیه خواهد شد. |  | 01/2294/218268 | 1401/06/19 | احتراما در ویرایش D01 مدرک مشخص گردیده است.
3 | مدرک ITP پیشنهادی کلیه سازندگان به همراه مدارک ارسال گردد. |  | 01/2294/218268 | 1401/06/19 | احتراما در ویرایش D01 مدرک انجام گردید.
4 | مطابق با دستور العمل بازرسی خرید و ساخت کالا مرحله 7 به عنوان مثال ITP مورد اشاره در پیشنهاد فنی شرکت غرب فلنج در مدارک ارسالی وجود ندارد. |  | 01/2294/218268 | 1401/06/19 | احتراما در ویرایش D01 مدرک انجام گردید.
5 | مدارک ارسالی فاقد اطلاعات سازندگان کالا بوده و صرفا شامل فرمت TBE است. لذا این ترانسمیتال قابل بررسی نیست. |  | 01/2294/218268 | 1401/06/19 | احتراما در ویرایش D01 مدرک اطلاعات کلیه سازندگان لحاظ گردیده است.
6 | دلایل پذیرش مشروط شرکت استیل آراز در TBE مشخص نیست. |  | 01/2294/218268 | 1401/06/19 | احتراما در Note 2 انتهای جدول TBE اعلام گردیده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.Mousazadeh | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 01.Jun.2022 |  |  |  |  | Date: 01.Jun.2022