## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PR-DT-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1252 |  |  | Transmital Date: 8/6/2022
Document Title:Process Data Sheets For 1st Stage Gas Air Coolers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1252 |  |  | Transmital Date: 8/6/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0003_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | دمای طراحی کولر هوایی AE-2101 و کمپرسور C-2101 با دمای طراحی مندرج در جدول 4-1-5 مدرک process design criteria مطابقت ندارد. |  | 1401-2294-226250 | 1401/06/27 | باتوجه به بند اشاره شده توسط آن کارفرمای محترم دمای طراحی برای محدوده دمایی Between + 60 ºC and 343 ºC برابر با Max. Oper. Temp. +25 ºC می باشد. باتوجه به اینکه دمای خروجی از کمپرسور مرحله اول برابر با 124.8C می باشد لذا دمای طراحی برابر با 150C خواهد بود. این پیمانکار با توجه به پیشنهاد شرکت های سازنده کمپرسور و به منظور اطمینان از متریالی که توسط vendor انتخاب می شود دمای طراحی را 5C بیشتر از دمای محاسبه شده در نظر گرفته است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021