## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-SP-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1317 |  |  | Transmital Date:8/27/2022
Document Title: Duty Specification For Gas Dehydration Package |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-1317 |  |  | Transmital Date: 8/27/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
2 | در بخش Introduction، بر اساس سناریوهای کارکرد هم زمان بسته نم زدا و تخلیه به شبکه مشعل، حداکثر میزان Backpressure، تصحیح گردد. |  | BK-SUR-ENG-PCS-01-05764 | 2022-09-24 | با توجه به مذاکرات شفاهی حداقل میزان Backpressure برابر با 0.5 BARG در نظر گرفته شد.
6 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-05764 | 2022-09-24 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: