## Sheet 1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-SA-SP-0003-D03 |  |  |  |  | EPC Contractor Tr. No : BK-HD-PEDCO-T-1462 |  |  | Transmital Date: 08/OCT/2022
Document Title: SPECIFICATION FOR FIRE WATER SYSTEM |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-SF-TR-1462 |  |  | Transmital Date: 08/OCT/2022
[5 empty] | CRS No:NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0003-D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص بند 1 نامه این امور، لازم است در مدرک فوق نقاط تنظیم جهت پمپ ها بر اساس نقطه نظرات قبلی این امور اصلاح گردد. مضافا اینکه این موضوع در مدرک P&ID نیز اصلاح گردد. |  | 1401-2294-294116 | 1401/08/12 | اعمال گردید. در مدرک P&ID نیز اصلاح گردید.
2 | در خصوص بند 4 نامه این امور، قطر شلنگ های آب آتش نشانی "3/4 2 با اتصالات "1/2 2 ذکر گردد. |  | 1401-2294-294116 | 1401/08/12 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: