## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-PI-DW-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0919 |  |  | Transmital Date: 09 MAY 2022
Document Title: Plot Plan Drawing - W046S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-0919 |  |  | Transmital Date: 09 MAY 2022
[5 empty] | CRS No: NISOC-CRS-BK-W046S-PEDCO-110-PI-DW-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مختصات جغرافیایی گودال سوخت مطابق با صورتجلسه مندرج در بند قبل و بر اساس UTM نشان داده شود. |  | 01/2294/85192 | 1401/03/10 | احتراما نقطه نظر اعمال گردید.
| مظابق با اسناد پایه، مخزن آب آشامیدنی نشان داده شود. |  | 01/2294/85192 | 1401/03/10 | احتراما نقطه نظر اعمال گردید.
1 | دلایل تغییر ساختمان برق نسبت به اسناد پیمان مشخص گردد. |  | 01/2294/85192 | 1401/03/10 | احتراما آخرین ویرایش نقشه معماری ساختمان برق در مدرک به روز رسانی شد و در صورت به وجود آمدن هر تغییری در ابعاد و جزییات ساختمان مذکور در این مدرک نیز اعمال خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: G.Khisravizadegan F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 1401/03/10 |  |  |  |  | Date: 23-May-2022