## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0025 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1264 |  |  | Transmital Date: 8/10/2022
Document Title: Process Data Sheets For Flare KO Drum Pumps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1264 |  |  | Transmital Date: 8/10/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0025_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | لازم است دلیل تغییر نوع پمپ (Flare K.O Drum ) P-2201 به Vertical اعلام شود. |  | 1401-2294-233609 | 1401/06/31 | در صورت الزام استفاده از پمپ افقی جهت تامین NPSH لازم نیاز به حفر پیت تا عمق 8 متر میباشد.با توجه به بالا بودن آبهای سطحی امکان حفر پیت با عمقی تزدیک به8 متر مشکل زا میباشد. و علاوه بر مشکلات عملیاتی و ایمنی ,امکان سیل کردن پیت مشکل است. لذا استفاده از پمپ مذکور ضروری می باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: