## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0023 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1264 |  |  | Transmital Date: 8/10/2022
Document Title: Process Data Sheets For Closed Drain Pumps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1264 |  |  | Transmital Date: 8/10/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0023_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | فشار بخار تصحيح گردد. |  | BK-SUR-ENG-PCS-01-05519 | 2022-08-24 | اعمال گردید.
2 | فشار خروجي با فشار ورودي و اختلاف فشار تطابق ندارد. |  | BK-SUR-ENG-PCS-01-05519 | 2022-08-24 | فشار خروجی برابر با 7 بار گیج است. اختلاف فشار برابر با 7 بارگیج است. فشار ورودی 0 بارگیج است. در داده های فوق عدم همخوانی مشاهده نمی شود.
3 | نقطه نظرات ارائه شده در مدرك محاسبات هيدروليك در اين مدرك نيز اعمال گردد. |  | BK-SUR-ENG-PCS-01-05519 | 2022-08-24 | در بخش DISCHARG LINE PRESSURE DROP در مدرک Calculation note For Pump در محاسبات لحاظ گردیده است و نیز نتایج مربوطه در این مدرک نیز اعمال گردیده است.
4 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-05519 | 2022-08-24 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: